## Sheet1
No | Tag No | Graph | Remark | General Remark for All tag
1 | 23-ZSO-3200A | S3_GAS_COMPRESSOR_TRAIN2 | Blinking effect is not correct yet to confirm the 25 second opening of the valve | Start up overide should be added to start the gas compressor
2 | 23-ZSC-3200A | S3_GAS_COMPRESSOR_TRAIN2 | Blinking effect is not correct yet to confirm the 25 second opening of the valve | Valve Feed back is still not link with the Valve HMI
3 | 23-ZSO-3208A | S3_GAS_COMPRESSOR_TRAIN2 | Channel assignment is wrong
4 | 23-ZSC-3208A | S3_GAS_COMPRESSOR_TRAIN2 | Channel assignment is wrong
5 | 23-ZSO-3211A | S3_GAS_COMPRESSOR_TRAIN2 | Channel assignment is wrong
6 | 23-ZSC-3211A | S3_GAS_COMPRESSOR_TRAIN2 | Channel assignment is wrong
7 | 23-ZSO-3209 | S3_GAS_COMPRESSOR_TRAIN2 | Blinking effect is not correct yet to confirm the 25 second opening of the valve
8 | 23-ZSC-3209 | S3_GAS_COMPRESSOR_TRAIN2 | Blinking effect is not correct yet to confirm the 25 second opening of the valve
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32